## Sheet1
FYP Timeline
Task Name | Start Date | Duration | End Date
Basic WebSocket Echo Server | 2014-02-03 | 2 | 2014-02-05
Basic Node.JS Kerberos Authentication | 2014-02-05 | 3 | 2014-02-08
Basic Android Application Using Echo Server | 2014-02-05 | 1 | 2014-02-06
Basic Android Application Using Kerberos with Echo Server | 2014-02-10 | 2 | 2014-02-12
Basic MongoDB with Node.JS | 2014-02-12 | 2 | 2014-02-14
Selective Forwarding using Node.JS | 2014-02-14 | 7 | 2014-02-21
Basic Android Selective Forwarding Chat Client Style App | 2014-02-23 | 5 | 2014-02-28
Populate Server with Mock Data | 2014-03-03 | 5 | 2014-03-08
Basic App which authenticates and can then download Schedule | 2014-03-11 | 13 | 2014-03-24
App with Basic Core functionality | 2014-03-24 | 19 | 2014-04-12
0
0
0
0
0
0
0
Formulas:
End Date = [Start Date]+[Duration]